FLUTTER INTEGRATED PROJECT · 2026

# Work Breakdown Structure

SaveAMeal

Decomposing the project into deliverable work packages.

# About This Document

This Work Breakdown Structure (WBS) decomposes SaveAMeal into a hierarchical list of all work required between May 19 and June 5, 2026. It is organized in three levels:

Level 1 — Major phases of the project (e.g. Planning, Design, Backend, Frontend, Integration, Delivery)

Level 2 — Deliverables within each phase

Level 3 — Individual work packages with assigned owner (M1–M5)

#### Each Level 3 work package is the smallest unit of work — sized so a single team member can complete it in a clear timebox. Work packages map directly to the rows of the Wideband Delphi Backlog (separate spreadsheet) and the bars of the Gantt chart (separate spreadsheet).

Owner Legend: M1	Tech Lead / Backend - Nang Hayman Aye Mya

M4	Driver Workflow + Beneficiary Confirm - Nichapa Jongsakulsiri

M2    Donor Workflow - Khin Nadi Ko

M3	Driver Map & Maps - Chotiya Khawsanga

M5	Shared Widgets, State, Beneficiary Status - Warisara Luechairam

# Work Breakdown Structure

## Planning & Design (May 19 – May 21)

### Concept & Scope Lock

    - Finalize concept document & lock feature scope	M1

    - Confirm Firebase as backend & document trade-offs	M1

    - Define non-functional requirements (performance, online-only, language)	M1

### Personas & Journey Maps

    - Donor persona & journey (Khun Siriporn)	M2

    - Driver persona & journey (Nattapong)	M3

    - Beneficiary persona & journey (Sister Maria)	M5

    - Cross-persona insights write-up	M1

### Figma Prototype

    - Design system: colors, typography, components, spacing	M5

    - Login Screen M1

    - Role Router / loading state M1

    - Donor Dashboard M2

    - Log Surplus Batch Form M2

    - QR Code Display M2

    - Driver Map Screen M3

    - Job Detail Screen M3

    - Pickup Checklist Screen M4

    - Delivery Confirmation Screen M4

    - Beneficiary Status Screen M5

    - Confirm Receipt Screen M4

    - Prototype linking & review walkthrough	M5

### Architecture Documents

    - Conceptual architecture diagram (3-sided marketplace)	M1

    - Implementation architecture (Flutter + Firebase + Maps)	M1

    - Firestore data model design (users, batches, pickups)	M1

### Planning Artifacts

    - Work Breakdown Structure (this document)	M1

1.5.2 Wideband Delphi backlog with effort estimates M1

1.5.3 Gantt chart for May 22 – June 5 M1

1.6 Submission 1 Package

1.6.1 Assemble all documents into final package M1

1.6.2 Team review & sign-off before May 21 noon M1

1.6.3 Submit by May 21, 12:00 PM M1

## Project Setup (May 22 – May 23)

2.1 Repository & Tooling

2.1.1 Create GitHub repo, set branch protection on main M1

2.1.2 Initialize Flutter project (flutter create saveameal) M1

2.1.3 Configure .gitignore, README, contribution guidelines M1

2.1.4 Create feature branches for each member M1

2.1.5 Set up shared folder structure per architecture M1

2.2 Firebase Setup

2.2.1 Create Firebase project (resqu-dev) M1

2.2.2 Enable Authentication (email/password)	M1

2.2.3 Provision Firestore (test rules, then locked rules)	M1

2.2.4 Provision Firebase Storage for photo uploads M1

2.2.5 Configure Firebase Cloud Messaging for push notifications M1

2.2.6 Run FlutterFire CLI configuration M1

2.2.7 Seed test data (3 donors, 5 drivers, 2 beneficiaries) M1

2.3 External APIs & Keys

2.3.1 Obtain Google Maps API key, configure billing alerts M3

2.3.2 Configure Maps for Android & iOS in Flutter M3

2.3.3 Store API keys securely (not committed to repo)	M1

2.4 State Management & Shared Foundation

2.4.1 Choose & configure state management (Provider) M5

2.4.2 Define shared data models (User, Batch, Pickup) M1

2.4.3 Build Firebase service layer (CRUD helpers) M1

## Shared Infrastructure (May 22 – May 26)

3.1 Authentication Flow

3.1.1 Build Login Screen UI	M1

3.1.2 Wire login to Firebase Auth M1

3.1.3 Build sign-up screen with role selection (demo only) M1

3.1.4 Implement Role Router M1

3.1.5 Implement "stay logged in" / session persistence M1

3.1.6 Logout flow & error handling M1

3.2 Shared Widget Library

3.2.1 Primary button, secondary button, danger button M5

3.2.2 Status badge component (Accepting / Full / Pending) M5

3.2.3 Impact metric card (kg, meals, CO2) M5

3.2.4 Job/batch card component M5

3.2.5 Loading spinner & empty-state widgets	M5

3.2.6 Star rating widget (1–5) M5

3.3 QR Services

3.3.1 QR generation utility (using qr_flutter) M2

3.3.2 QR scanner utility (using mobile_scanner) M4

3.3.3 Manual batch-ID entry fallback for failed scans M4

3.4 Push Notifications

3.4.1 FCM token registration on login M1

3.4.2 Cloud Function: notify driver when job posted (stretch — may use Firestore trigger) M1

3.4.3 Cloud Function: notify donor when driver accepts M1

3.4.4 Cloud Function: notify beneficiary on incoming delivery M1

3.4.5 Notification handling & deep-linking M1

## Donor Role Implementation (May 24 – May 28)

4.1 Donor Dashboard

4.1.1 Build dashboard layout with impact counters M2

4.1.2 Aggregate live metrics from Firestore (kg, meals, CO2) M2

4.1.3 Recent donations list M2

4.1.4 "Log Surplus Batch" CTA button M2

4.2 Log Surplus Batch

4.2.1 Build form UI: category, quantity, expiry, photo M2

4.2.2 Form validation (required fields, expiry future-date) M2

4.2.3 Photo capture / picker (camera + gallery) M2

4.2.4 Photo upload to Firebase Storage	M2

4.2.5 Write Batch document to Firestore (status = "open")	M2

4.3 QR Code Display

4.3.1 Generate QR from Firestore batch ID M2

4.3.2 Display batch summary alongside QR M2

4.3.3 "Done" / "Back to Dashboard" flow M2

## Driver Role Implementation (May 24 – May 30)

5.1 Driver Map Screen

5.1.1 Integrate Google Maps Flutter plugin	M3

5.1.2 Request & handle location permissions	M3

5.1.3 Center map on user location	M3

5.1.4 Fetch active batches from Firestore (status = "open")	M3

5.1.5 Render batch pins on the map	M3

5.1.6 Pin info window with quick batch summary	M3

5.2 Job Detail & Acceptance

5.2.1 Build job detail screen UI	M3

5.2.2 Display donor + beneficiary addresses, food details	M3

5.2.3 "Accept Job" button — atomic Firestore update (status = "claimed")	M3

5.2.4 "Open in Google Maps" external navigation	M3

5.3 Pickup Checklist

5.3.1 Pickup screen with QR scanner launcher	M4

5.3.2 Build 3-item safety checklist UI	M4

5.3.3 Photo upload confirmation	M4

5.3.4 Update Firestore batch status = "picked_up"	M4

5.4 Delivery Confirmation

5.4.1 Delivery screen with QR scan at beneficiary	M4

5.4.2 Delivery photo upload	M4

5.4.3 Update Firestore batch status = "delivered"	M4

5.4.4 "Job Complete" celebration screen with impact stats	M4

5.5 Driver Location Broadcasting

5.5.1 Periodic location write to Firestore while job active	M3

5.5.2 Cleanup on job complete or cancel	M3

## Beneficiary Role Implementation (May 26 – May 30)

6.1 Beneficiary Status Screen

6.1.1 Build status toggle UI (Accepting / Full)	M5

6.1.2 Persist status to Firestore beneficiary doc	M5

6.1.3 Incoming delivery banner (when batch assigned to them)	M5

6.1.4 Live driver location map (Firestore snapshots())	M5

6.1.5 ETA calculation from driver location → shelter	M5

6.2 Confirm Receipt

6.2.1 Build receipt confirmation UI	M4

6.2.2 1–5 star rating capture	M4

6.2.3 Optional comment field	M4

6.2.4 Write rating + close batch in Firestore	M4

## Integration & Testing (May 31 – June 3)

7.1 End-to-End Integration

7.1.1 Connect Donor → Driver flow (batch posting → claim)	M1

7.1.2 Connect Driver → Beneficiary flow (delivery → confirmation)	M1

7.1.3 Test push notifications end-to-end across roles	M1

7.1.4 Cross-role full transaction smoke test	M1

7.2 Manual QA & Bug Fixes

7.2.1 Donor flow regression test	M2

7.2.2 Driver flow regression test	M3

7.2.3 Beneficiary flow regression test	M5

7.2.4 Triage & fix critical bugs	M4

7.2.5 UI polish to match Figma exactly	M5

7.3 Edge Case Handling

7.3.1 Test offline / poor connectivity behaviors	M3

7.3.2 Test QR scan failure fallback	M4

7.3.3 Test concurrent driver acceptance (race condition)	M1

7.3.4 Verify Firestore security rules	M1

## Final Delivery (June 4 – June 5)

8.1 Demo Preparation

8.1.1 Prepare 3 demo accounts & seed data	M1

8.1.2 Rehearse 3-minute demo script	M1

8.1.3 Prepare 3 devices for live demo (donor / driver / beneficiary)	M3

8.1.4 Dry-run demo with full team	M1

8.2 Final Report

8.2.1 Write final report (brief summary of work)	M1

8.2.2 "Future Work" section listing dropped features	M2

8.2.3 Screenshots & impact metrics for the report	M5

8.2.4 Final review & sign-off	M1

8.3 Code Submission Package

8.3.1 Code freeze on main branch	M1

8.3.2 Tag final release v1.0-submission M1

8.3.3 Generate code zip from GitHub	M1

8.3.4 Verify git access is accessible to professor	M1

8.3.5 Submit final package by June 5	M

# WBS Summary

| Phase Name Window Key Deliverables |  |  |  |
| --- | --- | --- | --- |
| 1.0 | Planning & Design | May 19 – May 21 | Concept doc, personas, journeys, Figma, WBS, Gantt, backlog, architecture |
| 2.0 | Project Setup | May 22 – May 23 | GitHub, Flutter project, Firebase, Maps API, state, shared models |
| 3.0 | Shared Infrastructure | May 22 – May 26 | Auth, widget library, QR utilities, push notifications |
| 4.0 | Donor Role | May 24 – May 28 | Dashboard, Log Batch, QR Display |
| 5.0 | Driver Role | May 24 – May 30 | Map, Job Detail, Pickup, Delivery |
| 6.0 | Beneficiary Role | May 26 – May 30 | Status, Confirm Receipt |
| 7.0 | Integration & Testing | May 31 – June 3 | End-to-end flows, manual QA, bug fixes, edge cases |
| 8.0 | Final Delivery | June 4 – June 5 | Demo prep, final report, code submission |

How This WBS Connects to Other Documents

Wideband Delphi Backlog (spreadsheet) — Each Level 3 work package is one row, with three independent estimates and a final consensus estimate.

Gantt Chart (spreadsheet) — Each Level 2 deliverable is a bar with start date, end date, owner, and dependencies on the timeline.

Concept Document v2 — Defines the 13 features and screens that this WBS implements.

Personas & Journey Maps — Validates that every work package serves at least one of the three personas.